## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Design system architecture and technology stack | MUST HAVE | None | RACHANA | 3-Completed
S1 | S1 | US-002 | Design database schema for users, projects and tasks | MUST HAVE | US-001 | PARTHA | 3-Completed
S1 | S1 | US-003 | Create student registration and login module | MUST HAVE | US-002 | AKSHAYA | 3-Completed
S1 | S1 | US-004 | Create student profile and onboarding interface | MUST HAVE | US-003 | RACHANA | 3-Completed
S1 | S1 | US-005 | Create project idea submission and academic template module | MUST HAVE | US-004 | PARTHA | 3-Completed
S2 | S2 | US-006 | Develop feasibility analysis and project scoring module | MUST HAVE | US-005 | AKSHAYA | 3-Completed
S2 | S2 | US-007 | Develop project scope definition and task recommendation module | MUST HAVE | US-006 | RACHANA | 3-Completed
S2 | S2 | US-008 | Develop REST API endpoints for project management | MUST HAVE | US-002 | PARTHA | 3-Completed
S2 | S2 | US-009 | Develop project and task management interface | MUST HAVE | US-008 | AKSHAYA | 3-Completed
S2 | S2 | US-010 | Develop sprint planning and backlog management module | SHOULD HAVE | US-009 | PARTHA | 3-Completed
S3 | S3 | US-011 | Develop weekly check-in and milestone tracking module | MUST HAVE | US-010 | SURYA | 3-Completed
S3 | S3 | US-012 | Develop AI chatbot for academic project assistance | MUST HAVE | US-008 | PARTHA | 3-Completed
S3 | S3 | US-013 | Develop AI-based project risk assessment module | MUST HAVE | US-006 | AKSHAYA | 3-Completed
S3 | S3 | US-014 | Develop AI-based plan and task recommendation module | MUST HAVE | US-007 | RACHANA | 3-Completed
S3 | S3 | US-015 | Develop academic document generator | SHOULD HAVE | US-009 | PARTHA | 3-Completed
S4 | S4 | US-016 | Integrate Google authentication and OAuth | SHOULD HAVE | US-003 | SURYA | 3-Completed
S4 | S4 | US-017 | Develop student project progress dashboard | MUST HAVE | US-011 | AKSHAYA | 3-Completed
S4 | S4 | US-018 | Develop mentor monitoring and feedback dashboard | MUST HAVE | US-017 | DHESIGA | 3-Completed
S4 | S4 | US-019 | Implement notifications and reminders | SHOULD HAVE | US-011 | RACHANA | 3-Completed
S4 | S4 | US-020 | Perform system integration and testing | MUST HAVE | US-018 | AKSHAYA | 3-Completed
S4 | S4 | US-021 | Deploy and evaluate the complete platform | MUST HAVE | US-020 | RACHANA | 3-Completed
Note on F1: : ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 154 | 60 | 60 | 20 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Design student registration and profile onboarding interface | 2026-07-01 | 2026-07-04 | RACHANA | Architecture | 3-Completed | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Develop project proposal submission form with required fields | 2026-07-02 | 2026-07-06 | PARTHA | Database | 3-Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 3 | Build AI-based project feasibility analysis module | 2026-07-03 | 2026-07-08 | AKSHAYA | Design/UI | 3-Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 4 | Develop project scope and objective generation feature | 2026-07-06 | 2026-07-09 | RACHANA | Design/UI | 3-Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 5 | Create AI-generated project task and milestone planner | 2026-07-07 | 2026-07-10 | PARTHA | Coding | 3-Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 6 | Design project dashboard for students | 11-Jul-2026 | 15-Jul-2026 | AKSHAYA | Design/UI | 3-Completed | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 7 | Develop technology stack and milestone recommendation agent | 13-Jul-2026 | 17-Jul-2026 | RACHANA | Coding/AI | 3-Completed | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 8 | Build REST API endpoints for project management | 15-Jul-2026 | 20-Jul-2026 | PARTHA | Backend API | 3-Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 9 | Develop multi-agent project planning and action trigger system | 17-Jul-2026 | 22-Jul-2026 | AKSHAYA | Design/UI | 3-Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 10 | Implement real-time project progress and activity tracking | 20-Jul-2026 | 24-Jul-2026 | SURYA | Coding | 3-Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 11 | Build active project summary and status dashboard | 25-Jul-2026 | 29-Jul-2026 | PARTHA | Coding | 3-Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 12 | Develop weekly check-in and progress status system | 27-Jul-2026 | 31-Jul-2026 | AKSHAYA | Coding/AI | 3-Completed | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 13 | Implement backend chat interface for project context | 29-Jul-2026 | 03-Aug-2026 | RACHANA | Backend API | 3-Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | 14 | Build AI mentor chat UI with quick action prompts | 01-Aug-2026 | 05-Aug-2026 | PARTHA | Design/UI | 3-Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | 15 | Develop risk assessment and fallback recommendation engine | 03-Aug-2026 | 07-Aug-2026 | SURYA | Coding/AI | 3-Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | 16 | Build document exporter for synopsis, methodology, and slides | 08-Aug-2026 | 12-Aug-2026 | AKSHAYA | Coding | 3-Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | 17 | Develop system integration and final presentation preparation module | 10-Aug-2026 | 15-Aug-2026 | DHESIGA | Architecture | 3-Completed | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | 18 | Implement Google and GitHub OAuth single-click authentication | 13-Aug-2026 | 17-Aug-2026 | RACHANA | Backend/Auth | 3-Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | 19 | Reconfigure student command dashboard with KPI cards and launcher grid | 15-Aug-2026 | 2026-08-19 | AKSHAYA | Design/UI | 3-Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | 20 | Conduct end-to-end system testing and unit test case verification | 18-Aug-2026 | 2026-08-21 | RACHANA | Testing | 3-Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: : ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: : ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: : ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: : ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: : ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: : ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: : ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: : ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: : ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: : ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: : ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: : ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: : ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: : ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: : ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: : ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: : ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 07-Jul-2026 | Initial database schema and student profile requirements were not finalized. | Discussed requirements and clarified the student profile flow.
Sprint 1 | 10-Jul-2026 | Difficulty integrating the registration interface with the project proposal module. | Finalized the database schema and required fields.
Sprint 2 | 21-Jul-2026 | AI feasibility analysis required additional testing and API responses were inconsistent. | Refined the registration interface and tested the user flow.
Sprint 2 | 24-Jul-2026 | Project planning and milestone generation required refinement. | Tested AI prompts and improved feasibility analysis.
Sprint 3 | 04-Aug-2026 | Multi-agent planning caused delays in task execution and response processing. | Added API validation and improved error handling.
Sprint 3 | 07-Aug-2026 | Real-time progress tracking and weekly check-in data needed synchronization. | Updated milestone generation and verified project tasks.
Sprint 4 | 18-Aug-2026 | Document export and final system integration required verification | Optimized multi-agent planning and action triggers.
Sprint 4 | 21-Aug-2026 | Final testing identified minor UI and authentication issues. | Improved progress tracking and synchronized status updates.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint (M1) | 2026-07-01 | 2026-07-10 | RACHANA | Define registration | Unclear requirements | Requirement discussion | Finalized profile flow
2 | Sprint (M1) | 2026-07-01 | 2026-07-10 | PARTHA | Design database | Repeated schema changes | Database validation | Finalized database
3 | Sprint (M1) | 2026-07-01 | 2026-07-10 | AKSHAYA | Improve UI | Static layouts | User-friendly UI | Completed registration UI
4 | Sprint (M1) | 2026-07-01 | 2026-07-10 | SURYA | Validate proposal | Missing fields | Form validation | Completed proposal form
5 | Sprint (M1) | 2026-07-01 | 2026-07-10 | RACHANA | Review onboarding | Late updates | Team coordination | Verified M1
6 | Sprint (M2) | 2026-07-11 | 2026-07-24 | AKSHAYA | Plan project scope | Manual planning | Milestone planning | Refined project scope
7 | Sprint (M2) | 2026-07-11 | 2026-07-24 | PARTHA | Improve API | API errors | Backend validation | Implemented APIs
8 | Sprint (M2) | 2026-07-11 | 2026-07-24 | AKSHAYA | Design planner | Generic components | Consistent UI | Improved planner UI
9 | Sprint (M2) | 2026-07-11 | 2026-07-24 | SURYA | Test AI analysis | Single prompts | API testing | Improved AI analysis
10 | Sprint (M2) | 2026-07-11 | 2026-07-24 | PARTHA | Review AI output | Unverified outputs | Output checking | Verified M2
11 | Sprint (M3) | 2026-07-25 | 2026-08-07 | RACHANA | Track progress | Unsynced data | Progress updates | Implemented tracking
12 | Sprint (M3) | 2026-07-25 | 2026-08-07 | PARTHA | Improve chat backend | Invalid chat inputs | API testing | Completed chat backend
13 | Sprint (M3) | 2026-07-25 | 2026-08-07 | AKSHAYA | Improve mentor UI | Plain chat layout | Quick actions | Completed mentor UI
14 | Sprint (M3) | 2026-07-25 | 2026-08-07 | SURYA | Improve risk analysis | Ignoring edge cases | Fallback testing | Improved risk engine
15 | Sprint (M3) | 2026-07-25 | 2026-08-07 | RACHANA | Generate documents | Plain formatting | Structured reports | Completed exporter
16 | Sprint (M4) | 2026-08-08 | 2026-08-21 | RACHANA | Plan integration | Unverified integration | System validation | Completed integration
17 | Sprint (M4) | 2026-08-08 | 2026-08-21 | PARTHA | Improve authentication | Manual login | OAuth sync | Completed OAuth
18 | Sprint (M4) | 2026-08-08 | 2026-08-21 | AKSHAYA | Improve dashboard | Empty space | KPI dashboard | Updated dashboard
19 | Sprint (M4) | 2026-08-08 | 2026-08-21 | SURYA | Expand testing | Untested routes | Automated testing | Verified test cases
20 | Sprint (M4) | 2026-08-08 | 2026-08-21 | DHESIGA | Improve monitoring | Static cards | Interactive feedback | Completed faculty dashboard