## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | RACHANA | 2026-07-02 | Student registration form did not validate some required profile fields. | Sprint 1 | PARTHA | Logical | Added required-field validation and corrected profile validation logic. | 2026-07-03 | Closed | Registration validation tested successfully.
2 | PARTHA | 2026-07-03 | Database schema caused missing fields in student profile records. | Sprint 1 | RACHANA | Logical | Updated profile schema and database field mapping. | 2026-07-04 | Closed | Student profile data stored correctly.
3 | AKSHAYA | 2026-07-04 | Registration interface had inconsistent alignment and input spacing. | Sprint 1 | AKSHAYA | User Interface | Corrected form layout and responsive styling. | 2026-07-05 | Closed | UI verified across screen sizes.
4 | SURYA | 2026-07-06 | Project proposal form accepted incomplete submissions. | Sprint 1 | SURYA | Logical | Added form validation and submission checks. | 2026-07-07 | Closed | Incomplete proposals are now rejected.
5 | RACHANA | 2026-07-08 | Project scope generation produced incomplete objectives. | Sprint 1 | SURYA | Logical | Refined scope and objective generation prompts. | 2026-07-09 | Closed | Generated objectives verified.
6 | RACHANA | 2026-07-13 | AI feasibility analysis returned inconsistent responses for similar projects. | Sprint 2 | SURYA | Logical | Improved prompt handling and added response validation. | 2026-07-15 | Closed | AI feasibility results became consistent.
7 | PARTHA | 2026-07-15 | Project management API returned errors for invalid project requests. | Sprint 2 | PARTHA | Logical | Added request validation and error handling. | 2026-07-17 | Closed | API tested with valid and invalid requests.
8 | AKSHAYA | 2026-07-16 | Task and milestone planner displayed duplicate task cards. | Sprint 2 | AKSHAYA | User Interface | Corrected task rendering and duplicate handling. | 2026-07-18 | Closed | Task cards displayed correctly.
9 | SURYA | 2026-07-18 | AI milestone recommendations were not mapped correctly to project scope. | Sprint 2 | SURYA | Logical | Updated recommendation mapping logic. | 2026-07-20 | Closed | Milestone recommendations verified.
10 | PARTHA | 2026-07-21 | Project dashboard did not refresh after task status updates. | Sprint 2 | PARTHA | Logical | Added automatic status synchronization. | 2026-07-23 | Closed | Dashboard updates correctly.
11 | RACHANA | 2026-07-27 | Real-time progress tracking displayed outdated task information. | Sprint 3 | PARTHA | Logical | Improved progress data synchronization. | 2026-07-29 | Closed | Real-time progress verified.
12 | PARTHA | 2026-07-29 | Backend chat interface failed to retain project context. | Sprint 3 | PARTHA | Logical | Added project-context handling to chat requests. | 2026-07-31 | Closed | Context retained across chat requests.
13 | AKSHAYA | 2026-07-30 | AI mentor chat interface had unclear quick-action buttons. | Sprint 3 | AKSHAYA | User Interface | Improved button labels and quick-action layout. | 2026-08-01 | Closed | Quick actions verified.
14 | SURYA | 2026-08-01 | Risk assessment engine did not handle some fallback scenarios. | Sprint 3 | SURYA | Logical | Added fallback rules and error handling. | 2026-08-03 | Closed | Risk scenarios tested successfully.
15 | RACHANA | 2026-08-03 | Document exporter produced inconsistent formatting in generated reports. | Sprint 3 | RACHANA | User Interface | Standardized document formatting and templates. | 2026-08-05 | Closed | Exported documents verified.
16 | RACHANA | 2026-08-10 | Final system integration caused inconsistencies between modules. | Sprint 4 | RACHANA | Integration | Updated module interfaces and integration handling. | 2026-08-12 | Closed | Integrated modules tested successfully.
17 | PARTHA | 2026-08-12 | Google and GitHub authentication failed for some login attempts. | Sprint 4 | PARTHA | Authentication | Corrected OAuth configuration and callback handling. | 2026-08-14 | Closed | OAuth login verified.
18 | AKSHAYA | 2026-08-14 | Student dashboard contained excessive empty space in KPI sections. | Sprint 4 | AKSHAYA | User Interface | Reconfigured dashboard cards and layout spacing. | 2026-08-16 | Closed | Dashboard layout improved.
19 | SURYA | 2026-08-17 | Some system routes were not covered during testing. | Sprint 4 | SURYA | Testing | Added missing unit and integration test cases. | 2026-08-19 | Closed | Test cases executed successfully.
20 | DHESIGA | 2026-08-19 | Faculty monitoring dashboard did not provide sufficient interactive feedback. | Sprint 4 | DHESIGA | User Interface | Added interactive monitoring and feedback components. | 2026-08-20 | Closed | Faculty dashboard verified.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others